3rd Transnational Project Meeting Minutes

MathE

2018-1-PT01-KA203-047361

Date: 2 – 3 December 2019

Venue: LIT - Moylish Park, Limerick, V94 EC5T - Ireland

Participating partners:

- EuroED (RO)

- Instituto Politécnico de Bragança (PT)

- Kaunas University of Technology (LT)

- Limerick Institute of Technology (IE)

- Pixel (IT)

- University of Genova (IT)

Head of meeting: Ana I. Pereira, Instituto Politécnico de Bragança (PT)

Minutes taker: Lorenzo Martellini, Pixel (IT)

Table of contents

1.	Agenda	2

2.	List of Participants	3

3.	Minutes	3

- Agenda

| Date: | 2 – 3 December 2019 |
| --- | --- |
| Venue: | LIT - Moylish Park, Limerick, V94 EC5T – Ireland |

| 1 |  | Welcome of Participants |
| --- | --- | --- |
| 2 |  | Adoption of the agenda |
| 3 |  | Preparatory Activities: Involvement of target groups - Presentation of the results achieved |
| 4 |  | Presentation of the 3 Intellectual Outputs |
|  | 4.1 | Intellectual output 1: Student's Assessment Toolkit - Presentation of the current results and functionalities of the platform |
|  | 4.3 | Intellectual output 2: Online Math Library of Video Lessons and Teaching Materials - Presentation of the current results |
|  | 4.4 | Intellectual output 3: Community of Practice - Presentation of the planned activities and expected results |
| 5 |  | Presentation of the project’s events |
|  | 5.1 | Multiplayer events (ME) - Presentation of the templates for carrying out the activities (ME1 – 2 – 3 – 4) |
|  | 5.2 | Training Activity in Braganca (TA) - Presentation of the planned activities and expected results |
| 6 |  | Presentation of the Project Management Activities (PM) |
|  | 6.1 | Presentation and analysis of PM1: Coordination of Activities - Presentation of the current situation - Schedule of future meeting |
|  | 6.2 | Financial reporting of the project - Questions and answers session |
|  | 6.3 | Presentation and analysis of PM2: Dissemination - Presentation of the current results |
|  | 6.4 | Presentation and analysis of PM3: Exploitation - Presentation of the current results |
|  | 6.5 | Presentation and analysis of PM4: Evaluation - Presentation of the activities to be carried out |
| 7 |  | Any Other Business |
| 8 |  | Meeting Evaluation |

- List of Participants

| Name and Surname | Sending Organisation |
| --- | --- |
| Ana I. Pereira | Instituto Politécnico de Bragança (PT) |
| Arvid Perego | University of Genova (IT) |
| Carmen Antonita | EuroED (RO) |
| Daiva Petkevičiūtė-Gerlach | Kaunas University of Technology (LT) |
| Florbela Fernandes | Instituto Politécnico de Bragança (PT) |
| Lina Dindienė | Kaunas University of Technology (LT) |
| Lorenzo Martellini | Pixel (IT) |
| Marie Walsh | Limerick Institute of Technology (IE) |

- Minutes

- Welcome to Participants Marie Walsh from Limerick Institute of Technology (IE) welcomes all the project partners to Limerick and thanks them for coming at the meeting. She provides the partners with some practical information about facilities of the meeting room, social events accompanying the partners meeting and suggestions to enjoy their stay in Limerick. - Adoption of the agenda Lorenzo Martellini from Pixel (IT) explains the meeting folder. The meeting agenda is introduced and adopted by all partners. - Introduction to the project context and background Ana Isabel Pereira from Instituto Politécnico de Bragança (PT) presents MathE Project background. Students of scientific and economics subjects at higher education level often lack the basic maths skills to effectively follow their lectures. The target groups are: Math Lecturers Math Students at university level Policy Makers in the Field of Education The main project tangible results are 3 intellectual outputs: Students’ Assessment Toolkit Online Math Library of Video Lessons and Educational Material Teachers’ and Students’ Community of Practices Enhance the quality of teaching and improve pedagogies and assessment methods by: Facilitating the identification of students’ gaps in Math Providing Math teachers with appropriate digital sources Enhancing transnational sharing of innovative teaching sources - Preparatory Activities: Target Groups Involvement Actions to be Carried Out Involvement of target groups: - 25 lecturers - 100 students Templates and Tools PM1.A – Lecturer Information PM1.B – Student Information PM1.C – Role of the Target Groups Lorenzo Martellini presents the templates to the partners. The templates are analyzed, discussed, modified and approved asking to add a sentence related to the General Data Protection Regulation. The final version of the templates is attached to the minutes. Expected Results Each country should select and upload on the project portal at least: - 5 Lecturers - 20 Students Current Results Deadlines 15 December 2019 LIT (IE) Upload on the project portal the target group information - Presentation of the Intellectual Outputs of the MathE Project - Intellectual Output 1: Student's Assessment Toolkit Actions to be Carried Out IO1.1) Creation of all templates needed for carrying out the activities; 1 October 2018 15 October 2018. IO1.2) Development of the dedicated project portal section; 1 October 2018 30 November 2018. IO1.3) Definition of the questions for the Assessment Tools; 1 October 2018 30 June 2019. IO1.4) Review of the questions for the Assessment Tools; 1 April 2019 31 December 2019. Templates and Tools IO1.A – Assessment Tools Ten Math topics are identified and assigned to each partner as follows: - Manipulation of algebraic expressions (LIT) - Real Functions of a single variable (UniGenova) - Integration (IPB) - Matrix and determinats (KTU) - Linear systems (UniGenova) - Graphs (LIT) - Optimization (IPB) - Statistics (KTU) - Real Functions of several variables (TUIasi) - Differential equations (TUIasi) Expected Results - Identification of 10 Math topics - Distribution of 2 Math topics per partner - Each HEI partner for each of the 2 Math topics should define: - 40 questions/answer for the Student Need Assessment Tool - 20 questions/answer for the Student Assessment Tool - EuroED will give technical support to TUIasi Each HEI partner should review questions/answers for at least 3 Math topics. Current Results For Self Assessment Current Results For Final Assessment Deadlines 9 December 2019 HEIs Revision of the questions/answers produced for SNA 16 December 2019 TUIasi (RO) Definition for each of the 2 Math topics: - 20 questions/answer for the Student Final Assessment Tool 20 December 2019 HEIs Revision of the questions/answers produced for SNA - Intellectual output 2: Online MathE Library of Video Lessons and Teaching Materials Ana I. Pereira from Instituto Politécnico de Bragança (PT) presents the overview of the activities to be carried out in the framework of the Intellectual Output 2. Actions to be Carried Out IO2.1) Creation of all templates needed for carrying out the activities; 1 April 2019 30 April 2019. IO2.2) Identification and review of existing videos; 1 May 2019 31 August 2019. IO2.3) Production/adaptation of video lessons; 1 September 2019 31 January 2020. IO2.4) Production/adaptation of teaching material; 1 July 2017 30 July 2017. IO2.5) Review the proposed materials; 1 February 2020 30 May 2020. IO2.6) Preparation of the guide for the online version; 1 June 2020 30 September 2020. Templates and Tools IO2.A – Existing Video Review IO2.B – Video Lessons IO2.C – Teaching Material IO2.D – Teaching material review Templated IO2.A e IO2.B are presented, discussed, modified and approved. The approved version is attached to the minutes. Expected Results - Identification and review, by HEIs, of 5 existing videos for each of the 2 assigned topics - Production/adaptation, by HEIs*, of 5 video lessons for each of the 2 assigned topics - Production/adaptation, by each partner, of 10 Teaching material (podcast, pdf, …) for each of the 2 assigned topics * EuroED will take care of the video editing of the Romanian video lessons Current Results Each partner presents the video lesson produced. The video lessons are discussed and the partners agreed on their structure. The template for the teaching material is analysed, reviewed and approved. The final version is attached to the minutes and available in the download section of the web site. Deadlines 20 December 2019 TUIasi (RO) Identification and review of existing videos (5 per assigned topic or subtopic) 31 January 2020 HEIs and EuroED (RO) Production/adaptation of at least 1 video lesson 30 April 2020 HEIs and EuroED (RO) Production/adaptation of video lessons (5 per assigned topic) 30 May 2020 HEIs Production/ adaptation of 10 supporting learning material (podcast, pdf, …) for each assigned topic 15 June 2020 HEIs Review supporting learning material - Intellectual output 3: Community of Practice Ana I. Pereira from Instituto Politécnico de Bragança (PT) presents the overview of the activities to be carried out in the framework of the Intellectual Output 3. Actions to be Carried Out IO3.1) Creation of all templates needed for carrying out the activities; 1 May 2020 30 May 2020. IO3.2) Contribution to the community of practice from target groups; 1 June 2020 30 August 2020. IO3.3) Contribution to the community of practice from target groups related to good practice; 1 September 2020 30 October 2020. IO3.4) Production of the online guidebook of good practices; 1 November 2020 31 December 2020. IO3.5) Review the online guidebook of good practices; 1 January 2020 31 January 2020. IO3.1) Creation of all templates needed for carrying out the activities; 1 May 2020 30 May 2020. Ana Pereira from IPB (PT) gives a presentation of the purpose and the structure of the Community of practice. The presentation is attached. The teacher forum will have the following topics: - Experiments using MathE - Motivational tips in Math Subjects - Scientific publications in Math Educational Math teaching tools Activities using active based learning Partners can propose new topics. The student forum will be organised according to the topics and subtopics. Templates and Tools IO3.A – Structure of the Community IO3.B – Contribution Form IO3.C – Good Practice Form Expected Results - Active Community of Practice - Identification of good practices - Online guidebook of good practices Deadlines 31 January 2020 IPB (PT) Definition of the final list of the topics for the teachers` forum 31 January 2020 IPB (PT) MathE around the World 30 March 2020 EuroEd (RO) Guidebook – Part 1: MathE usability 30 May 2020 Pixel (IT) Teacher/Student Forum 30 October 2020 All HEIs Guidebook – Part 2: MathE experiments 30 November 2020 EuroEd (RO) Guidebook Edition - Presentation of the project’s events Lorenzo Martellini from Pixel (IT) presents the multiplier events which are foreseen in project. - Multiplayer events (ME) Actions to be Carried Out Organisation of a 5 dissemination events at national level on the: - Student's Assessment Toolkit - Online Math Library of Video Lessons and Teaching Materials - Community of Practice Templates and Tools ME.1 - Multiplier Event Form ME.2 - Programme Template ME.3 - List of Participants Template ME.4 - Minutes form Expected Results 4 dissemination events LIT (IE), UniGenova (IT), KTU (LT), TUIasi (RO) - involvement of 20 lecturers/researchers/teachers/policy makers (only participants from organisations other than the beneficiaries) Project Final Conference: IPB (PT) - involvement of 40 participants lecturers/researchers/teachers/policy makers (only participants from organisations other than the beneficiaries) Deadlines 31 January 2021 HEIs Sending of documents related to the multiplier events - Training Activity (TA) Actions to be Carried Out - Organisation in Braganca of a training event: - Topics: efficient use of the IOs during the lesson and for self learning - Participants: 2 members of the staff per each HEIs - Period: 1 – 7 November 2020 - Duration: 7 days (including 2 travelling days) - Certification: ECTS credits according to the duration of the training course Templates and Tools - TA.1 – Register - TA.2 – Programme - TA.3 – Certificate - TA.4 – Contents for the Mobility Europass - TA.5 – Participants Profile - TA.6 – Report Deadlines: 30 May 2020 IPB (PT), Pixel (IT) Definition of the Contents for the Europass 30 July 2020 HEIs Identify 2 participants in the training activity Contact the National Europass Centre (link) to activate the Europass Mobility for each participant 30 October 2020 HEIs Elaborate some individual literature review 2 – 6 November 2020 IPB (PT) Delivery of the training activity and sending to Pixel of the related material (register and report on the training activity) 15 December 2020 IPB (PT) Sending to Pixel of supporting documents (Report on the training activity, Register of participants, Programme, Certificates) 15 December 2020 HEIs Sending to Pixel of supporting documents: copies of the Europass certificates, description of the participants profiles and selection methodology The Europass Mobility is document to record knowledge and skills acquired in another European country. It is for any person moving to a European country to learn or acquire a work experience, whatever their age or level of education. - Presentation of the Project Management Activities (PM) The project Management includes 4 different activities: Coordination of activities Dissemination Exploitation Quality and monitoring Plan - Presentation and analysis of PM1: Coordination of Activities Activity to be carried out Attendance to the partners meeting - 1st Meeting: Florence (IT), October 2018 - 2nd Meeting: Kaunas (LT), May 2019 - 3rd Meeting: Limerick (IE), December 2019 - 4th Meeting: Braganca (PT), 25 – 26 June 2020 - 5th Meeting: Iasi (RO), February 2021 Production of project reports Template and Tools PM1.D – In progress activities reports PM1.E – Financial Manual (external annex) PM1.F – Financial Forms (external annex) PM1.G - Template of Mobility Declaration Current Results Expected Results Reports Production of: Three months period online Activities Reports Yearly Financial Report Deadlines Every three months (30 May 2020, 30 August 2020, 30 November 2020, 28 February 2020-2021) All Partners Production of Activities Report Forms 15 March 2021 All Partners Financial Reports - Project Management: PM2 – Dissemination Lorenzo Martellini explains the aim of dissemination events making examples of the main events that can be considered under dissemination purposes. Activity to be carried out Development and translation of project brochures Organization of at least 1 dissemination event on the project every month Creation of a Facebook page Production of the best practice dissemination report Production of transnational dissemination report Mobile version of the web site: http://host1.allyou.srl/00progetti/mathe/ Template and Tools Template: PM2.A – In progress dissemination reports Template: PM2.B – How to write the Best Practice Dissemination Report Lorenzo Martellini from Pixel (IT) shows the 2 templates and explains how to use and fill in them. Expected Results Project Brochure in all partners languages Database of dissemination events on the portal Facebook Page National Best Practice Dissemination Report Transnational Dissemination Report Current Results Deadlines Every three months (30 May 2020, 30 2020, 30 November 2019-2020, 28 February 2020-2021) All partners Upload of 1 dissemination events per month Every month All partners Contribution to the Facebook page 28 February 2021 All partners Final Best Practice Dissemination Report - Project Management: PM3 - Exploitation Lorenzo Martellini explains the aim of the exploitation which is to ensure that the project will continue after the funding period and that the intellectual outputs will be used by the end users in the future. In order to achieve this objective the partners will promote the portal and the intellectual outputs trough link on educational web sites. Partners will also involve associate partners that will give their support in the dissemination of the project intellectual outputs with their network of contacts. Actions to be Carried Out Involvement in the project of associated partners Collection of exploitation links Template and Tools PM3.A - Associated Partner Letter PM3.B - Associated Partner Information PM3.C – Exploitation links Lorenzo Martellini presents the Template and Tools and the partners approve them. Expected Results Involvement of 6 associated partners Collection of 6 exploitation links Current Results Deadlines 31 December 2019 All Partners Involvement of 1 associated partners Collection of 1 exploitation links 31 March 2020 All Partners Involvement of 3 associated partners Collection of 3 exploitation links 15 February 2021 All Partners Involvement of a total number of 6 associated partners Collection of a total number of 6 exploitation links - Presentation and analysis of PM4: Quality and Monitoring Plan Lorenzo Martellini from Pixel (IT) presents the idea under the current Activity. Actions to be carried out - Collection of testimonials - Production of testing evaluation report - Production of transnational evaluation report Template and Tools - PM4.A – Quality Plan - PM4.B – Project Meeting Evaluation Questionnaire (partners) - PM4.C – Project Evaluation Questionnaire (partners) - PM4.D – Evaluation Questionnaires for Intellectual Outputs (end users) - PM4.E – Tool for questionnaires analysis - PM4.F – How to write the Evaluation Report on Intellectual Outputs Expected Results - 3 issues of the Quality Plan - 6 testimonials per country - 20 evaluation questionnaires per country - 1 Testing Evaluation Report per country Deadlines 31 January 2021 All Partners Collection of 6 testimonials Collection of 20 evaluation questionnaires Sending of evaluation report on the IOs - Calendar of Activities and Reminder on Project Deadlines Lorenzo Martellini from Pixel (IT) presents all the deadlines foreseen for the project. It is agreed that all the partners have a week in order to propose changes to deadlines. The reviewed calendar of activities and calendar of deadlines will be enclosed to the meeting minutes as annexes. - Schedule of Future Meetings All partners agree to have the third partners’ meeting on 25 – 26 June in Braganca (PT) - Any Other Business Since there are no further matters for discussion, Lorenzo Martellini from Pixel (IT) thanks all participants for attending the meeting and he then declares the end of the meeting. - Meeting Evaluation Lorenzo Martellini from Pixel (IT) distributes to all partners the evaluation form that will be used to report their impressions on the meeting. Annexes: Annex 1 - Project presentation Annex 2 - Community of Practice Annex 3 - Calendar of deadlines Annex 4 - IO2.F - Teaching Material