## Slide 1
MathE
Improve Math Skills in Higher Education
Sixth Partners’ Meeting
Online 23 June 2021

## Slide 2: Funding Programme
European Commission funded through the Portuguese National Agency the MathE project in the framework of the Erasmus+ Programme – Strategic Partnerships for Higher Education Action.
Project number: 2018-1-PT01-KA203-047361

## Slide 3: Expected Results
The main project tangible results are 3 intellectual outputs:
Students’ Assessment Toolkit
Online Math Library of Video Lessons and Educational Material
Teachers’ and Students’ Community of Practices

## Slide 4: Project Activities

## Slide 5: The Project at a Glance
Involvement of target groups | October 2018 – December 2018
Student's Assessment Toolkit | October 2018 – December 2019
Online Math Library of Video Lessons and Teaching Materials | March 2019 – December 2020
Teachers’ and Students’ Community of Practice | January 2021 – June 2021
Training Actvity | June 2021
Multiplier Events | June 2021
Notes: 5

## Slide 6: Preparatory Activity (part of the Project Management) Target Groups Involvement

## Slide 7: PM1: Project Management 1/3 Actions to be Carried Out
Involvement of target groups:
  25 lecturers
  100 students

## Slide 8: PM1: Project Management 2/3 Expected Results
Each partner should select and upload on the project portal at least:
  5 Lecturers
  20 Students

## Slide 9: PM1: Project Management 3/3 Current Results
Partner | Lecturers | Students
IE_LIT | 11 | 64
IT_UniGenova | 8 | 169
LT_KTU | 9 | 168
PT_IPB | 24 | 470
Ro_UniIasi | 8 | 43
Others* | 19 | 10
 | 79 (25) | 954 (100)
* Others (e.g.)
Universidade do Minho (PT)
Escola Superior de Tecnolgia et Gestao (PT)
Hanze University of Applied Sciences (NL)
Liceo Scientifico Leonardo Da Vinci (IT)
Saint Petersburg University (RU)
Universidad de Zaragoza (ES)
Universidad de Zaragoza (ES)
Universidade de Coimbra (PT)
Expected numbers are indicated between brackets

## Slide 10: Intellectual Output 1 Student's Assessment Toolkit

## Slide 11: IO1: Student's Assessment Toolkit 1/12 Actions to be Carried Out
IO1.1) Creation of all templates needed for carrying out the activities | 1 October 2018 15 October 2018
IO1.2) Development of the dedicated project portal section | 1 October 2018 30 November 2018
IO1.3) Definition of the questions for the Assessment Tools | 1 October 2018 30 June 2019
IO1.4) Review of the questions for the Assessment Tools | 1 April 2019 31 December 2019

## Slide 12: IO1: Student's Assessment Toolkit 2/12 Templates and Tools
IO1.A – Assessment Tools

## Slide 13: IO1: Student's Assessment Toolkit 3/12 Expected Results
Identification of 10 Math topics
Distribution of 2 Math topics per HEI
Each HEI partner for each of the 2 Math topics should define:
  40 questions/answer for the Student Need Assessment Tool
  20 questions/answer for the Student Assessment Tool
EuroED will give technical support to TUIasi
Each HEI partner should review questions/answers for at least 3 Math topics

## Slide 14: IO1: Student's Assessment Toolkit 4/12
Manipulation of algebraic expressions (LIT)
Trigonometric functions
Real Functions of a single variable (UniGenova)
Differentiation
Integration (IPB)
Matrix and determinats (KTU)
Geometrical interpretation
EigenValues and EigenVectores
Linear systems (UniGenova)
Complex Numbers
Graphs (LIT)
Optimization (IPB)
Limits and sequences
Statistics (KTU)
Real Functions of several variables (TUIasi)
Differential equations (TUIasi)
First Proposal of Topics
Web Services
MathJax
https://www.mathjax.org/
Guppy
https://guppy.js.org/site/

## Slide 15: IO1: Student's Assessment Toolkit 8/12 Current Results/Self Assessment
Partner | To be evaluated | Approved
IE_LIT | 0 | 102
IT_UniGenova | 0 | 80
LT_KTU | 0 | 80
PT_IPB | 0 | 727
RO_UniIasi | 0 | 114
Tot | 0 | 1103
Uploaded Questions

## Slide 16: IO1: Student's Assessment Toolkit 9/12 Current Results/Self Assessment
Topic/Subtopic | Questions submitted | Questions approved | Questions reviewed | Questions to be reviewed
Analytical Geometry (IPB) | 40 | 40 | 40 (UniGe) | 
Complex Numbers (IPB) | 43 | 41 | 43 (UniGe) | 
Differential equations (TUIasi) | 42 | 41 | 42 (IPB) | 
Differentiation |  |  |  | 
Derivatives (LIT) | 47 | 46 | 47 (IPB) | 
Implicit Differentiation and Chain Rule (IPB) | 19 | 18 | 19 | 
Partial differentiation (IPB) | 68 | 64 | 68 (IPB) | 
Fundamental Mathematics |  |  |  | 
Elementary Geometry (IPB) | 48 | 47 | 48 (LIT) | 
Expressions and Equations (LIT) | 41 | 40 | 41 (IPB) | 
Graphs Theory (IPB) | 53 | 48 | 53 (TUIasi) | 

## Slide 17: IO1: Student's Assessment Toolkit 9/12 Current Results/Self Assessment
Topic/Subtopic | Questions submitted | Questions approved | Questions reviewed | Questions to be reviewed
Integration |  |  |  | 
Double Integration (IPB) | 41 | 40 | 41 (IPB) | 
Integration Techniques (IPB) | 42 | 41 | 42 (KTU) | 
Definite Integrals (IPB) | 44 | 44 | 44 (IPB) | 
Linear Algebra |  |  |  | 
Eigenvalues and Eigenvectors (IPB) | 40 | 40 | 40 (IPB) | 
Linear systems (UniGenova) | 51 | 51 | 51 (IPB) | 
Linear Transformations (IPB) | 40 | 40 | 40 (TUIasi) | 
Matrices and Determinants (KTU) | 41 | 40 | 41 (LIT) | 
Vector Spaces (IPB) | 40 | 40 | 40 (UniGE) | 
Numerical Methods(IPB) | 35 | 35 | 35 (IPB) | 

## Slide 18: IO1: Student's Assessment Toolkit 10/12 Current Results/Self Assessment
Topic/Subtopic | Questions submitted | Questions approved | Questions reviewed | Questions to be reviewed
Optimization |  |  |  | 
Linear Optimization (IPB) | 47 | 47 | 47 (TUIasi) | 
NonLinear Optimization (TUIasci + IPB) | 47 | 47 | 47 (TUIasi, LIT) | 
Probability | 46 | 46 | 46 (KTU) | 
Real functions of single variables (UniGe) |  |  |  | 
Domain, Image and Graphics | 17 | 17 | 17 (KTU) | 
Limits and Continuity | 25 | 25 | 25 (KTU) | 
Real functions of several variables (TUIasi) |  |  |  | 
Limits, Continuity, Domain and Image ((TUIasci + IPB) | 54 | 53 | 54 (LIT) | 
Statistics (KTU) | 40 | 41 | 40 (IPB) | 
Set Theory (IPB) | 40 | 40 | 40 (IPB) | 

## Slide 19: IO1: Student's Assessment Toolkit 8/12 Current Results/Final Assessment
Partner | To be evaluated | Approved | Submitted
IE_LIT | 0 | 49 | 49
IT_UniGenova | 0 | 40 | 40
LT_KTU | 0 | 40 | 40
PT_IPB | 0 | 290 | 290
RO_UniIasi | 0 | 67 | 67
Tot | 0 | 486 | 486
Uploaded Questions

## Slide 20: IO1: Student's Assessment Toolkit 9/12 Current Results/Final Assessment
Topic/Subtopic | Questions submitted | Questions approved | Questions reviewed | Questions to be reviewed
Analytical Geometry (IPB) | 22 | 20 | 22 (UniGe) | 
Complex Numbers (IPB) | 20 | 20 | 20 (UniGe) | 
Differential equations (TUIasi) | 20 | 17 | 17 (IPB) | 
Differentiation |  |  |  | 
Derivatives (LIT) | 27 | 27 | 27 (IPB) | 
Implicit Differentiation and Chain Rule | 12 | 11 | 12 (IPB) | 
Partial differentiation (IPB) | 15 | 14 | 15 (IPB) | 
Fundamental Mathematics |  |  |  | 
Elementary Geometry (IPB) | 20 | 20 | 20 (LIT) | 
Expressions and Equations (LIT) | 23 | 23 | 23 (IPB) | 
Graphs Theory (IPB) | 21 | 21 | 21 (TUIasi) | 

## Slide 21: IO1: Student's Assessment Toolkit 9/12 Current Results/Final Assessment
Topic/Subtopic | Questions submitted | Questions approved | Questions reviewed | Questions to be reviewed
Integration |  |  |  | 
Double Integration (IPB) | 20 | 20 | 20 (IPB) | 
Integration Techniques (IPB) | 20 | 20 | 20 (KTU) | 
Definite Integrals (IPB) | 23 | 23 | 0 (IPB) | 
Linear Algebra |  |  |  | 
Eigenvalues and Eigenvectors (IPB) | 20 | 20 | 20 (IPB) | 
Linear systems (UniGenova) | 20 | 20 | 20 (IPB) | 
Linear Transformations (IPB) | 20 | 20 | 20 (TUIasi) | 
Matrix and determinants (KTU) | 20 | 20 | 20 (LIT) | 
Vector Spaces (IPB) | 21 | 21 | 21 (UniGE) | 
Probability | 27 | 27 | 27 (KTU) | 

## Slide 22: IO1: Student's Assessment Toolkit 10/12 Current Results/Final Assessment
Topic/Subtopic | Questions submitted | Questions approved | Questions reviewed | Questions to be reviewed
Optimization |  |  |  | 
Linear Optimization (IPB) | 20 | 20 | 20 (TUIasi) | 
NonLinear Optimization (TUIasci + IPB) | 20 | 15 | 20 (TUIasi) | 
Probability | 27 | 27 | 27 (KTU) | 
Real functions of single variables |  |  |  | 
Domain, Image and Graphics (UniGe) | 12 | 12 | 12 (KTU) | 
Limits and Continuity (UniGe) | 8 | 8 | 8 (KTU) | 
Real functions of several variables |  |  |  | 
Limits, Continuity, Domain and Image (TUIasci + IPB) | 22 | 22 | 22 (LIT) | 
Set Theory (IPB) | 19 | 19 | 18 (IPB) | 
Statistics (KTU) | 20 | 20 | 20 (IPB) | 

## Slide 23: IO1: Student's Assessment Toolkit 12/12
The Intellectual Output is completed

## Slide 24: Intellectual Output 2 Online MathE Library of Video Lessons and Teaching Materials

## Slide 25: IO2: Online Math Library of Video Lessons …. 1/7 Actions to be Carried Out
IO2.1) Creation of all templates needed for carrying out the activities | 1 April 2019 30 April 2019
IO2.2) Identification and review of existing videos | 1 May 2019 31 August 2019
IO2.3) Production/adaptation of video lessons | 1 September 2019 31 January 2020
IO2.4) Production/adaptation of teaching material | 1 February 2020 30 May 2020
IO2.5) Review the proposed materials | 1 June 2020 30 September 2020

## Slide 26: IO2: Online Math Library of Video Lessons …. 2/7 Templates and Tools
IO2.A – Existing Video Review
IO2.B – Video Lessons
IO2.C - Video_Begin
IO2.D - Video_End
IO2.E – Guidelines for YouTube Channel
IO2.F – Teaching Material

## Slide 27: IO2: Online Math Library of Video Lessons …. 3/7 Expected Results
Identification and review, by HEIs, of 5 existing videos for each of the assigned topics or subtopics
Production/adaptation, by HEIs*, of 5 video lessons for each of the 2 assigned topics
Production/adaptation, by each partner, of 10 Teaching material (podcast, pdf, …) for each of the 2 assigned topics
* EuroED will take care of the video editing of the Romanian video lessons

## Slide 28: IO2: Online Math Library of Video Lessons …. 4/7 Current Results/Video Reviews
Partner | To be evaluated | Approved | Submitted
IE_LIT | 0 | 10 | 10
IT_UniGenova | 0 | 10 | 10
LT_KTU | 0 | 12 | 12
PT_IPB | 27 | 125 | 158
RO_UniIasi | 0 | 11 | 15
Tot | 0 | 168 (50) | 205
Uploaded Reviews

## Slide 29: IO2: Online Math Library of Video Lessons …. 5/7 Current Results/Video Lessons
Partner | To be evaluated | Approved | Submitted
IE_LIT | 0 | 10 | 11
IT_UniGenova | 0 | 10 | 10
LT_KTU | 0 | 10 | 10
PT_IPB | 0 | 18 | 30
RO_UniIasi | 0 | 12 | 12
Tot | 0 | 60 (50) | 73
Uploaded Video Lessons

## Slide 30: IO2: Online Math Library of Video Lessons …. 6/7 Current Results/Teaching Resources
Partner | To be evaluated | Approved | Submitted
IE_LIT | 0 | 20 | 20
IT_UniGenova | 0 | 20 | 20
LT_KTU | 0 | 23 | 26
PT_IPB | 9 | 119 | 140
RO_UniIasi | 1 | 17 | 19
Tot | 3 | 198 (100) | 225
Uploaded Teaching Resources

## Slide 31: IO2: Online Math Library of Video Lessons …. 7/7
The Intellectual Output is completed

## Slide 32: Intellectual Output 3 Community of Practice

## Slide 33: IO3: Community of Practice … 1/7 Activities
IO3.A –Table of contents (To be developed)
IO3.B – Guidelines to create the publication contents (To be developed)
IO3.1) Creation of all templates needed for carrying out the activities | 1 December 2020 15 December 2020
IO3.2) Contribution to the community of practice from target groups | 15 January 2021 15 June 2021
IO3.3) Contribution to the community of practice from target groups related to good practice | 15 January 2021 15 June 2021
IO3.4) Production of the online guidebook of good practices | 15 March 2021 30 June 2021
IO3.5) Review the online guidebook of good practices | 1 May 2021 31 July 2021

## Slide 34: IO3: Community of Practice … 2/7 Templates and Tools
IO3.A –Table of contents (To be developed)
IO3.B – Guidelines to create the publication contents (To be developed)
IO3.A - Community of Practice Guideline
IO3.B - Community of Practice Admin Guideline
IO3.C – Good Practice form

## Slide 35: IO3: Community of Practice … 3/7 Expected Results
Active Community of Practice
Identification of good practices
Online guidebook of good practices

## Slide 36: IO3: Community of Practice … 4/7 Current Results
Students’ Community available at https://student-mathe.pixel-online.org
Lecturers’ Community available at https://teacher-mathe.pixel-online.org
Both communities support insertions of math functions according to https://katex.org/docs/supported.html

## Slide 37: IO3: Community of Practice … 5/7 Current Results
Discussions For Lecturers’ Community
Experiments using MathE (Ana - IPB)
Motivational tips in Math Subjects (Marcel - UniIasi)
Scientific publications in Math Educational (Arvid - UniGe)
Math teaching tools (Marie - LIT)
Activities using Activity-Based Learning (Kristina - KTU)
Possible tags
#MathEsuggestions; #finalassessment; #teach; #TELbased;
#selfassessment; #games; #videos; #learn;
#education; #inquirybased; #projectbased;
#Flippedclassroom
Contribute to the list of TAGS: https://docs.google.com/spreadsheets/d/1RyBu_EypqklvMWjuKnHcD3aYAlaBNE6Wp-v2qSAxt4Q/edit?usp=sharing
Discussions For Students’ Community
Topics on MathE (Fatima - IPB)

## Slide 38: IO3: Community of Practice … 6/7 Current Results
Discussions For Lecturers’ Community
Discussions For Students’ Community
Area | Discussions | Posts
Experiments using MathE | 2 | 16
Motivational tips in Math Subjects | 4 | 12
Scientific publications in Math Educational | 11 | 47
Math teaching tools | 10 | 40
Activities using Activity-Based Learning | 3 | 13
Area | Discussions | Posts
MathE Topics | 7 | 43

## Slide 39: IO3: Community of Practice … 7/7 Deadlines
30 June 2021
EuroEd (RO)
Guidebook Edition

## Slide 40: Multiplier Events

## Slide 41: Multiplier Events1/4 Actions to be Carried Out
Organisation of a 5 dissemination events at national level on the:
  Student's Assessment Toolkit
  Online Math Library of Video Lessons and Teaching Materials
  Community of Practice

## Slide 42: Multiplier Events 3/4 Templates and Tools
ME.1 – Multiplier Event Description
ME.2 – Multiplier Event Programme
ME.3 – Multiplier Event List of Participants
ME.4 – Multiplier Event Minutes
ME.5 – Virtual Multiplier Event Declaration
Notes: 42

## Slide 43: Multiplier Events 2/4 Expected Results
4 dissemination events
LIT (IE), KTU (LT), TUIasi (RO)
  involvement of 20 lecturers/researchers/teachers/policy makers (only participants from organisations other than the beneficiaries)
Project Final Conference:
IPB (PT)
  involvement of 40 participants lecturers/researchers/teachers/policy makers (only participants from organisations other than the beneficiaries)

## Slide 44: Multiplier Events 4/4 Deadlines
31 July 2021
LIT (IE), IPB (PT), UniIasi (RO), KTU (LT)
Sending of documents related to the multiplier events

## Slide 45: Training Activity

## Slide 46: C1 – Training course Objectives of the Training Course
  How to identify and assess students gaps in Math
  How to create effective TEL and digital based teaching sources for Math
  How to cooperate with international colleagues in the Community of Practice
  Training will have a total duration of 40 hours, including individual work by the participants
  Certification: ECTS credits according to the duration of the training course
Notes: 46

## Slide 47: C1 – Training course Training course schedule 14 – 18 June 2021
  DAY 1: Monday 14h-19h
  DAY 2: Tuesday 09h-13h and 14h-17h
  DAY 3: Wednesday: 09h-13h
  DAY 4: Thursday 09h-13h and 14h-17h
  DAY 5: Friday: 09h-13h
Notes: 47

## Slide 48: C1 – Training course Teamwork methodogies
Thematic Topics
  Assessment methods
  E-Learning Tools and Strategies
  Methodologies to teach math
  Strategies to learn math
  Can include case studies in each topic
Each HEI will contribute with at least 2 lecturers, who should not be concentrated on just one topic.
Each topic should have a team between 3 - 5 participants.
Notes: 48

## Slide 49: C1 – Training course Current Results
The training activity took place online on 14-18 June 2021
Partner | Participants
IE_LIT | 5
IT_UniGenova | 2
LT_KTU | 2
PT_IPB | 10
RO_UniIasi | 5
Notes: 49

## Slide 50: C1 – Training course Template and Tools
TA.1 – Register
TA.2 – Programme
TA.3 – Certificate
TA.4 – Contents for the Mobility Europass
TA.5 – Participants Profile
TA.6 – Report
TA.7 - Training Activity Declaration
Notes: 50

## Slide 51: C1 – Training course Deadlines
15 July 2021
IPB (PT)
Sending to Pixel of supporting documents (Report on the training activity, Register of participants, Programme, Certificates, Declaration)
15 July 2021
HEIs
Sending to Pixel of the description of the participants profiles and selection methodology

## Slide 52: Project Management PM1 - Coordination of activities

## Slide 53: PM1 - Coordination of activities 1/5 Actions to be Carried Out
Attendance to the partners meeting
  1st Meeting: Florence (IT), October 2018
  2nd Meeting: Kaunas (LT), May 2019
  3rd Meeting: Limerick (IE), December 2019
  4th Online Meeting: 25 June 2020
  5th Online Meeting: 21 December 2020
  6th Online Meeting: 21 June 2021
Production of project reports

## Slide 54: PM1 - Coordination of activities 2/5 Templates and Tools
54
PM1.D – In progress activities reports
PM1.E – Financial Manual (external annex)
PM1.F – Financial Forms
PM1.G - Template of Mobility Declaration
Notes: 54

## Slide 55: PM1 - Coordination of activities 3/5 Expected Results
Production of:
Three months period online Activities Reports
Yearly Financial Report

## Slide 56: PM1 - Coordination of activities 4/5 Current Results
Partner | Online Activity Reports
IE_LIT | Updated 31 May 2021
IT_Pixel | Updated 31 May 2021
IT_UniGenova | Updated 31 May 2021
LT_KTU | Updated 31 May 2021
PT_IPB | Updated 22 June 2021
RO_EuroED | Updated 22 June 2021
RO_UniIasi | Updated 22 June 2021

## Slide 57: PM1 - Coordination of activities 5/5 Deadlines
All partners
Every three months (30 August 2021)
  Production of Activities Report Forms
15 September 2021
Financial Reports

## Slide 58: Project Management PM2 - Dissemination
Notes: 58

## Slide 59: PM2 - Dissemination 1/6 Actions to be Carried Out
  Development and translation of project brochures
  Organization of at least 1 dissemination event on the project every month
  Creation of a Facebook page
  Production of the best practice dissemination report
  Production of transnational dissemination report
  Mobile version of the web site
Notes: 59

## Slide 60: PM2 - Dissemination 2/6 Templates and Tools
  PM2.A – In progress dissemination reports
  PM2.B – How to write the Best Practice Dissemination Report
Notes: 60

## Slide 61: PM2 - Dissemination 3/6 Expected Results
Project Brochure in all partners languages
Database of dissemination events on the portal
Facebook Page
National Best Practice Dissemination Report
Transnational Dissemination Report
Notes: 61

## Slide 62: PM2 - Dissemination 4/6 Current Results
Partner | Number of Events (Last event) | Report
IE_LIT | 40 (18 June 2021) | OK
IT_Pixel | 94 (19 April 2021) | OK
IT_UniGenova | 32 (31 May 2021) | OK
LT_KTU | 36 (1 June 2021) | OK
PT_IPB | 42 (9 March 2021) | OK
RO_EuroED | 57 (22 March 2021) | 
RO_UniIasi | 26 (7 June 2021) | 

## Slide 63: PM2 - Dissemination 5/6 Deadline
Every three months (30 August 2021)
All partners
Upload of 1 dissemination events per month
30 June 2021
EuroED (RO), UniIasi (RO)
Best Practice Dissemination Report
Notes: 63

## Slide 64: Project Management PM3 - Exploitation
Notes: 64

## Slide 65: PM3- Exploitation 1/4 Actions to be Carried Out
  Involvement in the project of associated partners
  Collection of exploitation links
Notes: 65

## Slide 66: PM3- Exploitation 2/4 Templates and Tools
  PM3.A - Associated Partner Letter
  PM3.B - Associated Partner Information
  PM3.C - Exploitation links
Notes: 66

## Slide 67: PM3 - Exploitation 3/4 Expected Results
Involvement of 6 associated partners
Collection of 6 exploitation links
Notes: 67

## Slide 68: PM3 – Exploitation 4/6 Current Results
Partner | Associated Partners | Exploitation Links
IE_LIT | 6 | 5
IT_UniGenova | 6 | 8
LT_KTU | 3 | 6
PT_IPB | 2 | 3
RO_EuroED | 6 | 8
RO_UniIasi | 2 | 0
Registerd on the platform | 16* | 
Total | 38 | 20
*Platform
(UTFPR) - Campus de Curitiba (Brazil)
(UTFPR) - Campus de Ponta Grossa (Brazil)
HAW Hamburg (Germany)
Liceo M.L King di Genova (Italy)
Liceo Scientifico Leonardo Da Vinci (Italy)
Al-Farabi Kazakh National University (Kazakhstan)
Instituto Politécnico de Viana do Castelo (Portugal)
Politécnico do Porto (Portugal)
Universidade de Coimbra (Portugal)
Universidade de Trás-os-Montes e Alto Douro (Portugal)
Universidade do Minho (Portugal)
Saint Petersburg University (Russian Federation)
Universidad de Zaragoza (Spain)
Universitat Catalunya (Spain)
Hanze University of Applied Sciences (The Netherlands)
Aksaray University (Turkey)

## Slide 69: PM3: Exploitation 4/4 Deadlines
30 June 2021
UniIasi (RO)
Involvement of 3 associated partners
Collection of 3 exploitation links
30 June 2021
All Partners, but EuroED
Involvement of a total number of 6 associated partners
Collection of a total number of 6 exploitation links
Notes: 69

## Slide 70: Project Management PM4 - Quality and Monitoring Plan
Notes: 70

## Slide 71: PM4: Quality and Monitoring Plan 1/4 Actions to be Carried Out
  Collection of testimonials
  Production of testing evaluation report
  Production of transnational evaluation report
Notes: 71

## Slide 72: PM4: Quality and Monitoring Plan 2/4 Templates and Tools
  PM4.A – Quality Plan
  PM4.B – Project Meeting Evaluation Questionnaire (partners)
  PM4.C – Project Evaluation Questionnaire (partners)
  PM4.D – Evaluation Questionnaires for Intellectual Outputs (end users)
  PM4.E – Tool for questionnaires analysis
  PM4.F – How to write the Evaluation Report on Intellectual Outputs
Notes: 72

## Slide 73: PM4: Quality and Monitoring Plan 3/4 Expected Results
3 issues of the Quality Plan
6 testimonials per country
20 evaluation questionnaires per country
1 Testing Evaluation Report per country
Notes: 73

## Slide 74: PM4: Quality and Monitoring Plan 3/4 Current Results
Partner | XLS File | Report | Testimonials
IE_LIT | OK | OK | OK
IT_UniGenova | OK | OK | OK
LT_KTU | OK | OK | OK
PT_IPB |  |  | 
RO_EuroED &UniIasi | OK | OK | OK
Notes: 74

## Slide 75: TA4: Quality and Monitoring Plan 4/4 Deadlines
15 July 2021
IPB (PT)
Collection of 6 testimonials
Collection of 20 evaluation questionnaires
Sending of evaluation report on the IOs
Notes: 75

## Slide 76: Thank you for Your Attention
Questions?
Notes: 76