## Slide 1
Fiction
Functional ICT Instruction On the Net
First Partners’ Meeting
Florence, 28 – 29 November 2018

## Slide 2: Funding Programme
European Commission funded through the Swedish Council for Higher Education the Fiction project in the framework of the Erasmus+ Programme – Strategic Partnerships for School Education Action.
Project number: 2018-1-SE01-KA201-039098

## Slide 3: The Context
Digital tools increase students’ commitment and motivation for their studies.
Digital tools need to be used by teachers in the context of a well-reasoned pedagogy.

## Slide 4: Objective
The Fiction project has the aim the aim of enhancing teachers' knowledge to teach students to use digital tools for their own understanding of science.

## Slide 5: The Target Group
Policy Makers in the Field of Education
School directors
School Teachers
Students

## Slide 6: Expected Results
The main project tangible results are:
School teachers and directors guidelines
Competence Assessment tools
ICT learning objects as practice focus for participating teachers

## Slide 7: Project Activities

## Slide 8: The Project at a Glance
Involvement of target groups | November 2018 – January 2019
Guidelines to the use of ICT tools for science education | November 2018 – November 2019
Toolkit for innovative Science Teachers | August 2019 – September 2020
Training Actvity | June or September 2020
Multiplier Events | September 2020
Notes: 8

## Slide 9: Target Groups Involvement

## Slide 10: PM1: Project Management 1/4 Actions to be Carried Out
Involvement of target groups:
  12 schools
  42 science teachers

## Slide 11: PM1: Project Management 3/4 Templates and Tools
PM1.A – School Information
PM1.B – School letter
PM1.C – Role of the Target Groups
Notes: 11

## Slide 12: PM1: Project Management 2/4 Expected Results
Machiavelli (IT), Colaiste (IE) and Ronnaskolan (SE)
5 science teachers + English teachers (if needed for language support)
UniGenova (IT), LIT (IE) and SH (SE)
3 schools
9 science teachers + English teachers (if needed for language support)

## Slide 13: PM1: Project Management 4/4 Deadlines
30 April 2019
All Partners
Upload on the project portal the target group information

## Slide 14: Intellectual Output 1 Guidelines to the Use of ICT Tools for Science Education

## Slide 15: IO1: Guidelines 1/6 Actions to be Carried Out
IO1.1) Creation of all templates needed for carrying out the activities | 1 November 2018 15 November 2018
IO1.2) Development of the literature introduction | 1 December 2018 28 February 2019
IO1.3) Identification and description of case studies | 1 January 2019 31 March 2019
IO1.4) Teachers’ Interviews | 1 February 2019 30 April 2019
IO1.5) Transnational Comparison | 1 May 2019 30 June 2019
IO1.6) Production of guidelines for teachers | 1 May 2019 30 September 2019
IO1.7) Production of guidelines for school directors and policy makers | 1 May 2019 30 September 2019
IO1.8) Translation of guidelines for teachers and policy makers | 1 October 2019 30 November 2019

## Slide 16: IO1: Guidelines 2/6 Templates and Tools
IO1.A - Literature Introduction
IO1.B - Case Studies
IO1.C - Interviews
IO1.D - Guidelines

## Slide 17: IO1: Guidelines 3/6 Expected Results 1/2
1 Literature Review per country - UniGenova (IT), LIT (IE), SH (SE)
5 case studies - UniGenova and Machiavelli (IT), LIT and Colaiste (IE), SH and Ronnaskolan (SE)
5 interviews with science teachers - UniGenova and Machiavelli (IT), LIT and Colaiste (IE), SH and Ronnaskolan (SE)
Transnational comparison of specific needs of the different national systems SH (SE)

## Slide 18: IO1: Guidelines 4/6 Expected Results 2/2
Teachers’ Guidelines (coordinators)
Desirable digital competencies for teaching science – SH (SE),
Teachers’ self assessment - Genova University (IT),
Appropriate tools for professional development - Limerick Institute (IE)
Appropriate tools for teaching science using digital tools – ?
School Directors’ and Policy Makers’ Guidelines
Desirable digital competencies for teaching science
Existing gaps
Remedies
SH (SE), Genova University (IT), Limerick Institute (IE)

## Slide 19: IO1: Guidelines 5/6 Deadline
18 January 2019
SH (SE)
First draft of Chapter 1
1 February 2019
UniGenova (IT), LIT (IE), SH (SE)
Feedback on the first draft of Chapter 1
28 February 2019
UniGenova (IT), LIT (IE), SH (SE)
Development of the literature introduction (Chapter 1, 2 and 3.1)
31 March 2019
UniGenova and Machiavelli (IT) - LIT and Colaiste (IE) - SH and Ronnaskolan (SE)
Identification and description of case studies – production of paragraphs 3.2, 3.3, 3.4
30 April 2019
UniGenova and Machiavelli (IT) - LIT and Colaiste (IE) - SH and Ronnaskolan (SE)
interviews with science teachers – production of chapter 4

## Slide 20: IO1: Guidelines 6/6 Deadline
15 June 2019
SH (SE)
Transnational comparison (chapter 5)
30 October 2019
UniGenova and Machiavelli (IT) - LIT and Colaiste (IE) - SH and Ronnaskolan (SE)
Guidelines for teachers
30 October 2019
UniGenova (IT), LIT (IE), SH (SE)
Guidelines for school directors and policy makers
30 November 2019
UniGenova IT), SH (SE)
Translations of guidelines for teachers and policy makers in national language

## Slide 21: Intellectual Output 2 Toolkit for Innovative Science Teachers

## Slide 22: IO2: Toolkit for Innovative Science Teachers 1/4 Actions to be Carried Out
IO2.1) Creation of all templates needed for carrying out the activities | 1 August 2019 30 August 2019
IO2.2) Identification of desirable digital competences for teaching science | 1 October 2019 28 February 2020
IO2.3) Identification of tools for professional development in ICT and teachers’ self assessment | 1 October 2019 28 February 2020
IO2.4) Creation of ICT learning objects for science education | 1 March 2020 30 September 2020

## Slide 23: IO2: Toolkit for Innovative Science Teachers 2/4 Templates and Tools
IO2.A – Desirable digital competences for teaching science
IO2.B – Teachers’ self assessment
IO2.C – Appropriate tools for professional development
IO2.D – Appropriate tools for teaching science using digital tools

## Slide 24: IO2: Toolkit for Innovative Science Teachers 3/4 Expected Results
Database of competence assessment tools (at least 5 per country) and Tools for professional development (at least 5 per country)
UniGenova and Machiavelli (IT), LIT and Colaiste (IE), SH and Ronnaskolan (SE)
Database of existing ICT learning objects (at least 5 per country)
UniGenova and Machiavelli (IT), LIT and Colaiste (IE), SH and Ronnaskolan (SE)
Creation of ICT learning objects for science education (at least 5 per country)
Machiavelli (IT), Colaiste (IE) and Ronnaskolan (SE)
with the support of
UniGenova (IT), LIT (IE) and SH (SE)

## Slide 25: IO2: Toolkit for Innovative Science Teachers 4/4 Deadlines
30 August 2019
Pixel (IT), SH (SE)
Creation of the Templates
28 February 2020
All partners
Identification and review of competence assessment tools and tools for professional development
28 February 2020
All partners
Identification and review of existing ICT learning objects
30 September 2020
Machiavelli (IT), Colaiste (IE) and Ronnaskolan (SE)
Creation of ICT learning objects for science education

## Slide 26: Multiplier Events

## Slide 27: Multiplier Events1/4 Actions to be Carried Out
Organisation of a 3 dissemination events at national level in:
  Ireland
  Italy
  Sweden

## Slide 28: Multiplier Events 3/4 Templates and Tools
ME.1 – Multiplier Event Description
ME.2 – Multiplier Event Programme
ME.3 – Multiplier Event List of Participants
ME.4 – Multiplier Event Minutes
Notes: 28

## Slide 29: Multiplier Events 2/4 Expected Results
3 dissemination events
Machiavelli (IT), Colaiste (IE) and Ronnaskolan (SE)
  involvement of 20 teachers/policy makers (only participants from organisations other than the beneficiaries)

## Slide 30: Multiplier Events 4/4 Deadlines
30 September 2020
Machiavelli (IT), Colaiste (IE) and Ronnaskolan (SE)
Sending of documents related to the multiplier events

## Slide 31: Training Activity

## Slide 32: Training Activity 1/4 Actions to be Carried Out
Organisation at Södertörn University of a training event:
  Topics: efficient use of the IOs during the lesson and for self learning
  Participants: 3 members of the staff per each partner school involved
  Period: September 2020
  Duration: 7 days (including 2 travelling days)
  Certification: Europass Mobility and contents organised in learning units according to the ECVET model

## Slide 33: Training Activity 2/4 Template and Tools
TA.1 – Register
TA.2 – Programme
TA.3 – Certificate
TA.4 – Contents for the Mobility Europass
TA.5 – Participants Profile
TA.6 – Report
Notes: 33

## Slide 34: Training Activity 3/4 Deadlines 1/2
30 January 2020
SH (SE), Pixel (IT)
Definition of the:
Training Programme
Certificate for the participants
Contents for the Europass
30 May 2020
Machiavelli (IT), Colaiste (IE) and Ronnaskolan (SE)
Identify 3 participants in the training activity
Contact the National Europass Centre (link) to activate the Europass Mobility for each participant

## Slide 35: Training Activity 4/4 Deadlines 2/2
July 2020
SH (SE)
Delivery of the training activity
15 September 2020
SH (SE)
Sending to Pixel of supporting documents (Report on the training activity, Register of participants, Programme, Certificates)
15 September 2020
Machiavelli (IT), Colaiste (IE) and Ronnaskolan (SE)
Sending to Pixel of supporting documents: copies of the Europass certificates, description of the participants profiles and selection methodology

## Slide 36: Project Management PM1 - Coordination of activities

## Slide 37: PM1 - Coordination of activities 1/4 Actions to be Carried Out
Attendance to the partners meeting
  1st Meeting: Florence (IT), November 2018
  2nd Meeting: Limerick (IE), September 2019
  3rd Meeting: Genova (IT), February 2020
  4th Meeting: Stockholm (SE), October 2020
Production of project reports

## Slide 38: PM1 - Coordination of activities 3/4 Templates and Tools
38
PM1.D – In progress activities reports
PM1.E – Financial Manual (external annex)
PM1.F – Financial Forms
PM1.G - Template of Mobility Declaration
Notes: 38

## Slide 39: PM1 - Coordination of activities 2/4 Expected Results
Production of:
Three months period online Activities Reports
Yearly Financial Report

## Slide 40: PM1 - Coordination of activities 4/4 Deadlines
All partners
Every three months (30 January 2019-2020, 30 April 2019-2020, 30 July 2019-2020, 30 October 2019-2020)
  Production of Activities Report Forms
30 June 2019, 30 November 2019, 15 November 2020
Financial Reports

## Slide 41: Project Management PM2 - Dissemination
Notes: 41

## Slide 42: PM2 - Dissemination 1/5 Actions to be Carried Out
  Development and translation of project brochures
  Organization of at least 1 dissemination event on the project every month
  Creation of a Facebook page
  Production of the best practice dissemination report
  Production of transnational dissemination report
Notes: 42

## Slide 43: PM2 - Dissemination 3/4 Templates and Tools
  PM2.A – In progress dissemination reports
  PM2.B – How to write the Best Practice Dissemination Report
Notes: 43

## Slide 44: PM2 - Dissemination 3/5 Expected Results
Project Brochure in all partners languages
Database of dissemination events on the portal
Facebook Page
National Best Practice Dissemination Report
Transnational Dissemination Report
Notes: 44

## Slide 45: PM2 - Dissemination 4/5 Deadlines
Every three months (30 January 2019-2020, 30 April 2019-2020, 30 July 2019-2020, 30 October 2019-2020)
All partners
Upload an average of 1 dissemination event per month
Every month
All partners
Contribute to the Facebook page
30 December 2018
SH (SE)
Development of project brochure
Notes: 45

## Slide 46: PM2 - Dissemination 5/5 Deadlines
30 January 2019
All partners
Translation of project brochure
15 September 2019
All partners
Progress Best Practice Dissemination Report
15 September 2020
All partners
Final Best Practice Dissemination Report
Notes: 46

## Slide 47: Project Management PM3 - Exploitation
Notes: 47

## Slide 48: PM3- Exploitation 1/4 Actions to be Carried Out
  Involvement in the project of associated partners
  Collection of exploitation links
Notes: 48

## Slide 49: PM3- Exploitation 2/4 Templates and Tools
  PM3.A - Associated Partner Letter
  PM3.B - Associated Partner Information
  PM3.C - Exploitation links
Notes: 49

## Slide 50: PM3 - Exploitation 3/4 Expected Results
Involvement of 6 associated partners
Collection of 6 exploitation links
Notes: 50

## Slide 51: PM3: Exploitation 4/4 Deadlines
15 September 2019
All Partners
Involvement of 3 associated partners
Collection of 3 exploitation links
15 September 2020
All Partners
Involvement of a total number of 6 associated partners
Collection of a total number of 6 exploitation links
Notes: 51

## Slide 52: Project Management PM4 - Quality and Monitoring Plan
Notes: 52

## Slide 53: PM4: Quality and Monitoring Plan 1/4 Actions to be Carried Out
  Collection of testimonials
  Production of testing evaluation report
  Production of transnational evaluation report
Notes: 53

## Slide 54: PM4: Quality and Monitoring Plan 2/4 Templates and Tools
  PM4.A – Quality Plan
  PM4.B – Project Meeting Evaluation Questionnaire (partners)
  PM4.C – Project Evaluation Questionnaire (partners)
  PM4.D – Evaluation Questionnaires for Intellectual Outputs (end users)
  PM4.E – Tool for questionnaires analysis
  PM4.F – How to write the Evaluation Report on Intellectual Outputs
Notes: 54

## Slide 55: PM4: Quality and Monitoring Plan 3/4 Expected Results
3 issues of the Quality Plan
6 testimonials per country
20 evaluation questionnaires per country
1 Testing Evaluation Report per country
Notes: 55

## Slide 56: TA4: Quality and Monitoring Plan 4/4 Deadlines
15 September 2020
All Partners
Collection of 6 testimonials
Collection of 20 evaluation questionnaires
Sending of evaluation report on the IOs
Notes: 56

## Slide 57: Thank you for Your Attention
Questions?
Notes: 57