**Calendar of Deadlines**

**IO1 – Student's Assessment Toolkit**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 9 December 2019 | * Review of the questions for the assigned topic * Definition of keywords | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | Online Validation |
| 16 December 2019 | Definition for, each of the topics the partner is responsible of, of 20 questions/answer for the Final Assessment Tool | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | IO1.A – Assessment Tools |
| 20 December 2019 | Review of the questions for the assigned topic | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | Online Validation |

**IO2 – Online Math Library of Video Lessons and Teaching Materials**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partners Involved** | **Template and Tools** |
| 20 December 2019 | Identification and review, by each partner, of 5 existing videos for each assigned topics (at least 2 topics by HEI partner) | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | IO2.A – Existing Video Review |
| 31 January 2020 | Production/adaptation of at least 1 video lesson | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO)  EuroEd (RO): Video editing of the Romanian video lessons; | IO2.B – Video Lessons |
| 31 April 2020 | Production/adaptation, by each partner, of video lessons (5 for each assigned topic) | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO)  EuroEd (RO): Video editing of the Romanian video lessons; | IO2.B – Video Lessons |
| 30 May 2020 | Production/ adaptation, by each partner and for each assigned topic, of 10 Teaching material (podcast, pdf, …) | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | IO2.C – Teaching Material |
| 15 June 2020 | Review the proposed materials. Each HEI partner review all material of 3 math topics | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | IO2.D – Teaching material review |

**IO3 – Community of Practice**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partners Involved** | **Template and Tools** |
| 31 January 2020 | Definition of the final list of the topics for the teachers` forum | IPB (PT) |  |
| 31 January 2020 | MathE around the World | IPB (PT) |  |
| 30 March 2020 | Guidebook – Part 1: MathE usability | EuroEd(RO) |  |
| 30 May 2020 | Teacher/Student Forum | Pixel |  |
| 30 October 2020 | Guidebook – Part 2: MathE experimentation | EuroEd(RO) |  |
| 30 November 2020 | Guidebook edition | EuroED (RO) |  |

**Multiplier Events**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 31 January 2021 | Organisation of an event for 40 Portuguese lecturers/researchers/teachers/policy makers in order to present, discuss the project results and address their sustainability in the national system | IPB (PT) | ME.1 - Multiplier Event Form  ME.2 - Programme Template  ME.3 - List of Participants Template  ME.4 - Minutes form |
| 31 January 2021 | Organisation of an event for 20 (Italian/Romanian/Lithuanian/Irish) lecturers/researchers/teachers/policy makers in order to present, discuss the project results and address their sustainability in the national system. | LIT (IE), UniGenova (IT), KTU (LT), TUIasi (RO) | ME.1 - Multiplier Event Form  ME.2 - Programme Template  ME.3 - List of Participants Template  ME.4 - Minutes form |

**Training Activity**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 30 May 2020 | Definition of the Contents for the Europass | IPB (PT) |  |
| 30 July 2020 | Each partner should:   * Identify 2 participants in the training activity * Contact the National Europass Centre Contact the National Europass Centre ([link](https://europass.cedefop.europa.eu/about/national-europass-centres)) in order to activate the Europass Mobility for each participant. | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | TA.4 – Contents for the Mobility Europass |
| 30 October 2020 | Elaborate some individual literature review | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) |  |
| 2 – 6 November 2020 | Delivery of the training activity | IPB (PT) | TA.1 – Course Register Template  TA.2 – Programme Template  TA.3 – Certificate Template |
| 15 December 2020 | Sending to Pixel of supporting documents (Report on the training activity, Register of participants, Programme, Certificates) | IPB (PT) | TA.6 – Report |
| 15 Devember 2020 | Sending to Pixel of supporting documents: copies of the Europass certificates, description of the participants profiles and selection methodology | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | TA.5 – Participants Profile |

**Project Management**

|  |  |  |  |
| --- | --- | --- | --- |
| **PM1 - Coordination of Activities** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 15 December 2019 | Selection and involvement for testing activities, by each partner, of 20 students and 5 lecturers.  Upload on the project portal of the related information | LIT (IE) | PM1.A – Student Information  PM1.B – Lecturer Information  PM1.C – Role of the target groups |
| 28 February 2020-2021  30 May 2020, 30 August 2020  30 November 2020 | Production and Uploading of Project Activities Report | All partners | <https://mathe.pixel-online.org/MNG-wip.php> |
| 15 March 2021 | Production of Financial Reports | All partners | PM1.E – Financial Manual  PM1.F – Financial Forms |

|  |  |  |  |
| --- | --- | --- | --- |
| **PM2 - Dissemination** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 28 February 2020-2021  30 May 2020, 30 August 2020  30 November 2020 | Organization of 1 dissemination event on the project every month and uploading the dissemination events description on the project web site (every three months) | All partners |  |
| 15 February 2021 | Production of the progress Best Practice Dissemination Report | All partners | Template: PM2.B – How to write the Best Practice Dissemination Report |

|  |  |  |  |
| --- | --- | --- | --- |
| **PM3 - Exploitation** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 31 December 2019 | Upload on the project portal of 1 associated partner.  Sending to Pixel of 1 exploitation link | All partners |  |
| 31 March 2020 | Upload on the project portal a total number of 3 associated partners.  Sending to Pixel a total number of 3 exploitation links | All partners | PM3.A - Associated Partner Letter  PM3.B - Associated Partner Information |
| 15 February 2021 | Upload on the project portal a total number of 6 associated partners.  Sending to Pixel a total number of 6 exploitation links | All partners | PM3.C - Exploitation links |

|  |  |  |  |
| --- | --- | --- | --- |
| **PM4 - Quality and Monitoring Plan** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| February 2021 | * Collection of 2 testimonials * Collection of 20 evaluation questionnaires * Sending of evaluation report on the IOs | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), EuroEd (RO) | PM4.C – Teachers’ Evaluation Questionnaires for Intellectual Outputs  PM4.D – How to write the Evaluation Report on Intellectual Outputs |