**Calendar of Deadlines**

**IO1 – Student's Assessment Toolkit**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 20 July 2020 | Review of the questions for final assessment | UniGenova (IT, IPB (PT) | Online Validation |

**IO2 – Online Math Library of Video Lessons and Teaching Materials**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partners Involved** | **Template and Tools** |
| 30 November 2020 | Upload missing video lessons | All partner | IO2.B – Video Lessons |
| 30 November 2020 | Upload missing teaching resources | All partners, but LIT (IE) | IO2.C – Teaching Material |

**IO3 – Community of Practice**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partners Involved** | **Template and Tools** |
| 15 September 2020 | Production of template for good practice | Pixel and EuroED |  |
| 30 September 2020 | Suggest tags for discussions | HEIs | [Shared Google Sheet](https://docs.google.com/spreadsheets/d/1RyBu_EypqklvMWjuKnHcD3aYAlaBNE6Wp-v2qSAxt4Q/edit?usp=sharing) |
| 15 December 2020 | Identification of 2 good practices and upload them on the forum dedicated to “Experiments using MathE” | HEIs | IO3.B – Good Practice Form |
| 30 November 2020 | Guidebook edition | EuroED (RO) |  |

**Multiplier Events**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 3o June 2021 | Organisation of an event for 40 Portuguese lecturers/researchers/teachers/policy makers in order to present, discuss the project results and address their sustainability in the national system | IPB (PT) | ME.1 - Multiplier Event Form  ME.2 - Programme Template  ME.3 - List of Participants Template  ME.4 - Minutes form |
| 3o June 2021 | Organisation of an event for 20 (Italian/Romanian/Lithuanian/Irish) lecturers/researchers/teachers/policy makers in order to present, discuss the project results and address their sustainability in the national system. | LIT (IE), UniGenova (IT), KTU (LT), TUIasi (RO) | ME.1 - Multiplier Event Form  ME.2 - Programme Template  ME.3 - List of Participants Template  ME.4 - Minutes form |

**Training Activity**

|  |  |  |  |
| --- | --- | --- | --- |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 30 November 2020 | Definition of the Contents for the Europass | IPB (PT) |  |
| 31 January 2021 | Each partner should:   * Identify 2 participants in the training activity * Contact the National Europass Centre Contact the National Europass Centre ([link](https://europass.cedefop.europa.eu/about/national-europass-centres)) in order to activate the Europass Mobility for each participant. | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | TA.4 – Contents for the Mobility Europass |
| 30 March 2021 | Elaborate some individual literature review | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) |  |
| 12 – 16 April 2021 | Delivery of the training activity | IPB (PT) | TA.1 – Course Register Template  TA.2 – Programme Template  TA.3 – Certificate Template |
| 15 May 2021 | Sending to Pixel of supporting documents (Report on the training activity, Register of participants, Programme, Certificates) | IPB (PT) | TA.6 – Report |
| 15 May 2021 | Sending to Pixel of supporting documents: copies of the Europass certificates, description of the participants profiles and selection methodology | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), TUIasi (RO) | TA.5 – Participants Profile |

**Project Management**

|  |  |  |  |
| --- | --- | --- | --- |
| **PM1 - Coordination of Activities** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 30 August 2020, 30 November 2020, 28 February 2021, 30 May 2021, 30 August 2021 | Production and Uploading of Project Activities Report | All partners | <https://mathe.pixel-online.org/MNG-wip.php> |
| 15 September 2021 | Production of Financial Reports | All partners | PM1.E – Financial Manual  PM1.F – Financial Forms |

|  |  |  |  |
| --- | --- | --- | --- |
| **PM2 - Dissemination** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 30 August 2020, 30 November 2020, 28 February 2021, 30 May 2021, 30 August 2021 | Upload 1 dissemination event on the project web site (every three months) | All partners | <https://mathe.pixel-online.org/MNG-diss.php> |
| 30 June 2021 | Production of the progress Best Practice Dissemination Report | All partners | Template: PM2.B – How to write the Best Practice Dissemination Report |

|  |  |  |  |
| --- | --- | --- | --- |
| **PM3 - Exploitation** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 30 September 2020 | Involvement of 3 associated partners  Collection of 3 exploitation links | All partners | PM3.A - Associated Partner Letter  PM3.B - Associated Partner Information |
| 30 June 2021 | Upload on the project portal a total number of 6 associated partners.  Sending to Pixel a total number of 6 exploitation links | All partners | PM3.C - Exploitation links |

|  |  |  |  |
| --- | --- | --- | --- |
| **PM4 - Quality and Monitoring Plan** | | | |
| **Deadline** | **Results** | **Partner** | **Template and Tools** |
| 30 June 2021 | * Collection of 2 testimonials * Collection of 20 evaluation questionnaires * Sending of evaluation report on the IOs | LIT (IE), UniGenova (IT), KTU (LT), IPB (PT), EuroEd (RO) | PM4.C – Teachers’ Evaluation Questionnaires for Intellectual Outputs  PM4.D – How to write the Evaluation Report on Intellectual Outputs |