**Partners’ Role – LIT (IE)**

**Activities to be carried out related to**

**“IO1 – Guidelines to The Use Of ICT Tools For Science Education”**

**Activity IO1.2**

Provide Feedback on the first draft of Chapter 1.

**Expected results:** Feedback on the first draft of Chapter 1

**Start Date:** 18 January 2019

**End Date:** 1 February 2019

**Activity IO1.2**

Development of the literature introduction (Chapter 1, 2 and 3.1)

**Expected results:** Chapter 1, 2 and 3.1

**Start Date**: 1 December 2018

**End Date:** 28 February 2019

**Activity IO1.3**

Identification and description of case studies –production of paragraphs 3.2, 3.3, 3.4 of template IO1.A - Literature Introduction.

**Expected results:**

Availability of 5 case studies per country.

**Start Date:** 1 January 2019

**End Date:** 31 March 2019

**Activity IO1.4**

Interviews with science teachers –production of chapter 4 of template IO1.A - Literature Introduction.

**Expected results:**

Availability of 5 interviews per country.

**Start Date:** 1 February 2019

**End Date**: 30 April 2019

**Activity IO1.6**

Production of guidelines for teachers.

**Expected results:**

Guidelines for teachers in 4 chapters.

**Start Date**: 1 May 2019

**End Date:** 30 September 2019

**Activity IO1.7**

Production of guidelines for school directors and policy makers.

**Expected results:**

Guidelines for teachers in 3 chapters.

**Start Date**: 1 May 2019

**End Date**: 30 September 2019

**Activity IO1.8**

Translation of guidelines for teachers and policy makers.

**Expected results:**

Guidelines in national languages.

**Start Date**: 1 October 2019

**End Date**: 30 November 2019

**Activities to be carried out related to**

**“IO2 – Toolkit for Innovative Science Teachers”**

**Activity IO2.2**

Identification and review of competence assessment tools and tools for professional development.

**Expected results:**

Database of Identification and review of competence assessment tools and tools for professional development

(at least 5 per country).

**Start Date**: 1 October 2019

**End Date:** 28 February 2020

**Activity IO2.3**

Identification and review of existing ICT learning objects.

**Expected results:**

Database of ICT learning objects (at least 5 per country).

**Start Date**: 1 October 2019

**End Date:** 28 February 2020

**Activity IO2.4**

Creation of ICT learning objects for science education (at least 5 per country).

**Expected results:**

Collection of ICT learning objects for science education.

**Start Date**: 1 March 2020

**End Date:** 30 September 2020

**Activities to be carried out related to**

**“PM1 –Coordination of activities”**

**Activity PM1.2**

Participation in Partners Meetings.

1st Meeting: Florence (IT) 2nd Meeting: Limerick (IE)

3rd Meeting: Sodertorn (SE) 4th Meeting: Genova (IT)

**Time schedule:**

1° meeting: November 2018

2° meeting: September 2019

3° meeting: February 2020

4° meeting: October 2020

**Activity PM1.3**

Selection and involvement for testing activities, by each partner, of

* 3 schools
* 9 teachers + English teachers (if needed for language support)

Upload on the project portal of the School Presentation Forms

Sending to Pixel the scanned version of the school letters.

**Expected results:** Online Database of Schools.

**Start Date:** 1 December 2018

**End Date:** 30 January 2019

**Activity PM1.3**

In Progress reporting on activities

Production and Uploading of Project Activities Report Forms.

**Expected results by each partner:**

In progress Project Activities Report

**Time schedule:**

30 January 2019-2020

30 April 2019-2020,

30 July 2019-2020,

30 October 2019-2020

**Activity PM1.5**

Production of Project Financial Report.

**Expected results by each partner:** Project Financial Report

**Time schedule:**

Progress: 30 June 2019

Progress: 30 November 2019

Final: 15 November 2020

**Activities to be carried out related to**

**“PM2 – Dissemination”**

**Activity PM2.4**

Dissemination trough Facebook:

Partners must upload at least 1 post per month on the activities carried out at national level.

**Start Date:** 1 January 2019

**End Date:** 30 October 2020

**Activity PM2.6**

Organization of 1 dissemination event on the project every month and uploading the dissemination events description on the project web site.

**Expected results by each partner:**

Filling in of the dissemination form on the project web site (every three months).

**Time Schedule:**

30 January 2019-2020

30 April 2019-2020,

30 July 2019-2020,

30 October 2019-2020

**Activity PM2.7**

Production of the best practice dissemination report.

**Expected results by each partner:**

One progress and one final Best Practice Dissemination Report.

**End Date for Year 1:** 15 September 2019

**End Date for Year 2:** 15 September 2020

**Activities to be carried out related to**

**“PM3 – Exploitation”**

**Activity PM3.2**

Involvement in the project of at least 6 organizations (3 per year) operating in the field of education, who will join the project as associated partner filling in the Associate partner form. They will be also inserted as Associate Partners on the project portal.

**Expected results by each partner:**

- 4 letters of participation in the project as associate partners (2 per year)

- 4 Associate Partners template filled in (3 per year)

**End Date for Year 1:** 15 September 2019

**End Date for Year 2:** 15 September 2020

**Activity PM3.3**

Publication of announcements on 4 portals (2 per year) or websites addressed to teachers.

**Expected results by each partner:** 4 exploitation links (2 per year).

**End Date for Year 1:** 15 September 2019

**End Date for Year 2:** 15 September 2020

**Activities to be carried out related to**

**“PM4 - Quality and Monitoring Plan”**

**Activity PM4.3**

Evaluation of the Intellectual outputs:

* Collection of 2 testimonials
* Collection of 20 evaluation questionnaires
* Sending of evaluation report on the IOs

**Expected results:** National Evaluation Report

**Start Date**: 1 May 2020

**End Date**: 15 September 2020