**Partners’ Role – Pixel (IT)**

**Activities to be carried out related to**

**“IO1 – Guidelines to The Use Of ICT Tools For Science Education”**

**Activity IO1.1**

Creation of all templates needed for carrying out the activities.

Expected results:

Template IO1.A - Literature Introduction

Template IO1.B - Case Studies

Template IO1.C - Interview

Template IO1.D – Guidelines

Start Date: 1 November 2018

End Date: 15 November 2018

**Activities to be carried out related to**

**“IO2 – Toolkit for Innovative Science Teachers”**

**Activity IO2.1**

Creation of all the templates needed for carrying out the activities.

**Expected results:**

IO2.A – Desirable digital competences for teaching science

IO2.B – Teachers’ self assessment

IO2.C – Appropriate tools for professional development

IO2.D – Appropriate tools for teaching science using digital tools

**Start Date**: 1 August 2019

**End Date:** 30 August 2019

**Activities to be carried out related to**

**“TA – Training Activity”**

Activity TA1

Production of templates for the organisation of a 5 days training event in Sodertorn to train science teachers to the use of ICT learning objects for science education.

The training activity is scheduled for July 2020

**Expected results:**

Training Programme

Certificate for the participants

Definition of the contents for the Europass and of the EVET learning units.

**Start Date:** 1 January 2020

**End Date:** 30 January 2020

**Activities to be carried out related to**

**“PM – Project Management”**

**Activity PM1.1**

Creation of all the templates for carrying out the activities.

**Expected results:**

Template: PM1.A – School Information

Template: PM1.B – School letter

Template: PM1.C – Role of the school

Template: PM1.D – In progress activities reports

Template: PM1.E – Financial Manual

Template: PM1.F – Financial Forms

Template: PM1.G - Template of Mobility Declaration

**Start Date:** 1 November 2018

**End Date:** 15 November 2018

**Activity PM1.2**

Participation in Partners Meetings.

1st Meeting: Florence (IT) 2nd Meeting: Limerick (IE)

3rd Meeting: Sodertorn (SE) 4th Meeting: Genova (IT)

**Time schedule:**

1° meeting: November 2018

2° meeting: September 2019

3° meeting: February 2020

4° meeting: October 2020

**Activity PM1.3**

In Progress reporting on activities

Production and Uploading of Project Activities Report Forms.

**Expected results by each partner:**

In progress Project Activities Report**.**

**Time schedule:**

30 January 2019-2020

30 April 2019-2020,

30 July 2019-2020,

30 October 2019-2020

**Activity PM1.5**

Production of Project Financial Report.

**Expected results by each partner:**

Project Financial Report

**Time schedule:**

Progress: 30 June 2019

Progress: 30 November 2019

Final: 15 November 2020

**Activities to be carried out related to**

**“PM2 – Dissemination”**

**Activity PM2.1**

Creation of all the templates needed for carrying out the activities.

**Expected results**:

Template: PM2.A – In progress dissemination reports

Template: PM2.B – How to write the Best Practice Dissemination Report

**Start Date:** 1 November 2018

**End Date**: 15 November 2018

**Activity PM2.3**

Creation of a Facebook page.

**Expected results:**

Facebook page

**Start Date**: 1 December 2018

**End Date:** 30 December 2018

**Activity PM2.4**

Dissemination trough Facebook:

Partners must upload at least 1 post per month on the activities carried out at national level.

**Start Date:** 1 January 2019

**End Date:** 30 October 2020

**Activity PM2.6**

Organization of 1 dissemination event on the project every month and uploading the dissemination events description on the project web site.

**Expected results by each partner:**

Filling in of the dissemination form on the project web site (every three months).

**Time Schedule:**

30 January 2019-2020

30 April 2019-2020,

30 July 2019-2020,

30 October 2019-2020

**Activity PM2.7**

Production of the best practice dissemination report.

**Expected results by each partner:**

One progress and one final Best Practice Dissemination Report.

**End Date for Year 1:** 15 September 2019

**End Date for Year 2:** 15 September 2020

**Activities to be carried out related to**

**“PM3 – Exploitation”**

**Activity PM3.1**

Creation of all the forms, guidelines and documents needed for carrying out the activities.

**Expected results**:

Template: PM3.A - Associated Partner Letter

Template: PM3.B - Associated Partner Information

Template: PM3.C - Exploitation links

**Start Date:** 1 November 2018

**End Date:** 15 November 2018

**Activity PM3.2**

Involvement in the project of at least 6 organizations (3 per year) operating in the field of education, who will join the project as associated partner filling in the Associate partner form. They will be also inserted as Associate Partners on the project portal.

**Expected results by each partner:**

- 4 letters of participation in the project as associate partners (2 per year)

- 4 Associate Partners template filled in (3 per year)

**End Date for Year 1:** 15 September 2019

**End Date for Year 2:** 15 September 2020

**Activity PM3.3**

Publication of announcements on 4 portals (2 per year) or websites addressed to teachers.

**Expected results by each partner:** 4 exploitation links (2 per year).

**End Date for Year 1:** 15 September 2019

**End Date for Year 2:** 15 September 2020

**Activities to be carried out related to**

**“PM4 - Quality and Monitoring Plan”**

**Activity PM4.1**

Creation of templates needed for carrying out the activities.

**Expected results**:

Template: PM4.A – Quality Plan

Template: PM4.B – Project Meeting Evaluation Questionnaire

Template: PM4.C – Project Evaluation Questionnaire

Template: PM4.D – Teachers’ Evaluation Questionnaires for Intellectual Outputs

Template: PM4.E – Tool for questionnaires analysis

Template: PM4.F – How to write the Evaluation Report on Intellectual Outputs

**Start Date:** 1 November 2018

**End Date:** 15 November 2018

**Activity PM4.2**

Production of the issues of the Quality Plan.

**Expected results:**

3 issues of the Quality Plan.

**Time schedule:**

1st issues: November 2018

2nd issue: September 2019

3rd issue: September 2020